Brief project description

East Kalimantan Province in 2021/2022 received great attention nationally because of the moving of the state capital city (Jakarta) to a location near the city of Balikpapan and Penajam Paser Utara in East Kalimantan Province. The development of the new capital will start in 2022. Although the Indonesia President commit to develop the new capital as Forest and Smart City, the surrounding area particularly the coastal area such as Delta Mahakam and Adang Bay might get high pressure as the consequence of the new development and the movement of 1.5 million people to the new capital.

Delta Mahakam, in the eastern part of East Kalimantan, is an area that is relatively close to the prospective center of the State capital (about 100 km). Mahakam Delta is naturally a mangrove habitat, but due to excessive land clearing for extensive aquaculture about 47.5 % of the mangrove ecosystem is degraded to be converted into aquaculture (2017). Despite various conservation efforts by different parties and the government, land clearing still continues. Delta Mahakam land ownership is government land that has designated as a production forest, but this area has been inhabited by residents from generation to generation.

Adang Bay is one of the coastal villages in Adang Bay, Paser Regency, on the southern part of East Kalimantan Province (about 100 km from the new capital). This area is also experiencing land conversion to increase aquaculture, besides there are several locations in coastal areas that are affected by abrasion. Restoration activities in East Kalimantan Province are needed to restore a degraded environment, as well as to support the vision of the nation's capital as a green city.

The ecosystem in Delta Mahakam and Adang Bay are also home to critically endangered species, such as the nasal monkey (proboscis monkey), endemic to the island of Borneo. On a global scale, the mangrove is a key ecosystem to answer the challenge of carbon sequestration and fight against climate change.

The objective of the project is therefore to contribute to restore the degraded mangrove forest in East Kalimantan (Delta Mahakam and Adang Bay) as home of endemic and endangered species including proboscis monkey and key ecosystem to mitigate and to adapt the impact of climate change; and this, through four main actions: raising awareness of the stakeholders, rehabilitating degraded mangrove forest, supporting the development of sustainable livelihood, and strengthening the coastal governance.

Main Sustainable Development Goals (SDGs) to which the project contributes

Main SDG targets and indicators to which the project contributes:

- 12.8. By 2030, ensure that people everywhere have the relevant information and awareness for sustainable development and lifestyles in harmony with nature.

- 13.1. Strengthen resilience and adaptive capacity to climate-related hazards and natural disasters in all countries.

- 13.3. Improve education, awareness-raising, human, and institutional capacity on climate change mitigation, adaptation, impact reduction and early warning.

- 14.2. Sustainably manage and protect marine and coastal ecosystems to avoid significant adverse impacts, including by strengthening their resilience, and take action for their restoration in order to achieve healthy and productive oceans.

- 14. B. Provide access for small-scale artisanal fishers to marine resources and markets.

- 15.5. Take urgent and significant action to reduce the degradation of natural habitats, halt the loss of biodiversity, protect and prevent the extinction of threatened species.

| Project duration | 3 years (March 2023 – February 2026) |  |
| --- | --- | --- |
| Budget & funding |  |  |
| Total required resources (€) 2023-2026 | 818 341 € // 903 613 USD |  |
| Author(s) | YML, POKJA, Yayasan Planete Urgensi Indonesia, Planète Urgence |  |
| Approval by partners | Planète Urgence/Yayasan Planet Urgensi Indonesia | Name: Réonaldus Title: Indonesia National Delegate |
|  | YML | Name: Achmad Nuriyawan Title: Director |
|  | POKJA | Name: Hamsuri Title: The Board of Trustee |

Table of contents

1.	Implementing partner	2

2.	Context & environment and development challenges	3

Geographic and socio-economic context	3

Environmental context	4

Biodiversity issues	6

Environment and development challenges	8

3.	Strategy & theory of change	11

4.	Beneficiaries	12

5.	Location	13

6.	Expected results, planned activities & required resources	13

Output 1: The awareness of stakeholders to conserve Delta Mahakam and Adang Bay is strengthened.	14

Activity 1.1. Conduct workshops in schools of East Kalimantan province to raise awareness on environment and biodiversity preservation.	14

Activity 1.2. Support Adiwiyata School (Green School) in Delta Mahakam	15

Activity 1.3. Conduct public awareness campaigns to sensitize communities in East Kalimantan province to the ecological, economic and climatic benefits of the mangrove.	15

Output 2: 300 ha area of degraded mangrove forest are restored by planting 800.000 of mangrove tree.	17

Activity 2.1. Pres-assessment study on land suitability	17

Activity 2.2. Ensure establishment and management of community-based nurseries	17

Activity 2.3. Identify and prepare planting locations, and train local community members to mangrove restoration, and conduct tree planting.	18

Activity 2.4. Participatory Monitoring Training and ensure the monitoring and protection of targeted mangrove areas	20

Output 3. Alternative sustainable livelihoods in Delta Mahakam and Adang Bay are available, improved and shared to other key stakeholders in the region.	22

Activity 3.1. Establish demonstration plots for sustainable aquaculture (sustainable ponds and sylvo fishery models)	22

Activity 3.2. Train community groups particularly women group on the financial management and product marketing.	22

Output 4. The sustainable coastal governance in Delta Mahakam and Adang Bay are strengthened	23

Activity 4.1. Facilitate coordination meeting among Mahakam Delta and Adang Bay’s actors to synergize the program	23

7.	Partnerships	26

8.	Cross-cutting approaches	29

9.	Knowledge management, capitalization & communication	31

10.	Sustainability, scaling-up and/or exit strategy	36

11.	Results framework	38

12.	Monitoring & evaluation	42

13.	Timeline	44

- Implementing partner

Name of the organization: Yayasan Mangrove Lestari

Address: Jl. Pelita 3 RT.12 Gg.7 Kel. Sambutan Samarinda

Legal status: Akta notaris ; Nomor : 01 Tanggal 01 Juni 2012; Kemenkumham ; Nomor : AHU-3696.AH.01.04.2013

The Yayasan Mangrove Lestari Delta Mahakam (YML) is a local non-governmental organization based in Samarinda, East Kalimantan Province. Environmental activists and local communities with the purpose of helping the conservation of the mangrove ecosystem in the Mahakam Delta, East Kalimantan Province, founded this organization on February 21, 2012.

YML is open to collaborating with various parties who have the same goal of conserving the environment, especially the mangrove ecosystem. In its development, YML has collaborated with local governments and donor agencies including Planète Urgence in carrying out mangrove restoration activities.

YML has a vision to create a sustainable mangrove ecosystem that provides benefits to local communities. The mission of YML includes:

- Restoring mangrove ecosystems, especially in the Mahakam Delta

- Helping to realize sustainable aquaculture in the mangrove ecosystem area

- Assisting local communities in improving livelihood activities to increase family income

- Build partnerships with stakeholders for the conservation of mangrove ecosystems.

YML has an office in Samarinda with a field secretariat in Muara Badak, Delta Mahakam to help fish and shrimp farmer groups to practice sustainable aquaculture.

Name of the organization: Pokja Pesisir

Address: Tengiri VI Street No.10 RT.24 Kelurahan Manggar Baru, Kecamatan Balikpapan Timur, Kota Balikpapan, Kalimantan Timur 76114

Email: perkumpulanpokjapesisir@gmail.com

Tel: +62 813 4874 4716

Website: http://pokjapesisir.id/

Legal status: Legally Registered under the Ministry of Law and Human Rights, 2019 No 008760.AH.01.07 Tahun 2019

Kelompok Kerja Pesisir (The Coastal Area Working Group), commonly abbreviated as “Pokja Pesisir”, is a non-profit organization formed by a group of environmental activists in Balikpapan City, East Kalimantan Province. This organization was formed with the objective to raise public attention to preserve coastal and marine ecosystems that are rich in biodiversity, including clusters of mangrove areas, distribution of coral reefs and seagrass beds.

In addition, government policies towards fishermen communities also need to be continuously encouraged in order to be optimal for the welfare of fishermen. The lives of fishermen in coastal areas in East Kalimantan Province often experience difficulties due to the privatization of coastal areas, difficulties in obtaining fuel for fishing boats, and also low human resources.

Based on these issues, a group of activists agreed in 2009 to establish an organization which was later named the “Coastal and Fisherman Working Group”. This institution has been advocating policies for improving coastal and marine governance and carrying out empowerment actions for fishing communities. As an effort to preserve the coastal area, the “Coastal and Fishermen Working Group” initiated a program called Mangrove and Marine Protection Area in Teritip Village, East Balikpapan Sub-district, Balikpapan City, in collaboration with UNDP in 2009 – 2010. The Working Group then change the name to “Pokja Pesisir” and was legally registered at the Ministry of Law and Human Rights in 2018.

Some activities conducted by POKJA Pesisir:

- 2009 – 2010 mangrove and coastal area conservation in Teritip, Balikpapan (supported by UNDP).

- 2009 – 2016: community organizing in the coastal area of Balikpapan.

- 2016 – now: Monitoring and campaign on the protection of the highly conservation value in Balikpapan Bay

- 2016 – now: Community assistance on the conservation of Balipapan Bay

- March 2017 – January 2018, Implementing the Program of “Strengthening of CSO Network on Mangrove Conservation in Indonesia” in Balikpapan Bay.

- 2021 – March 2022, Proposing the Conservation area in coastal area and small islands of Balikpapan Bay (supported by TFCA)

In term of organization: a Board of Trustees, a Board of Supervisor and members, manage POKJA Pesisir.

- Context & environment and development challenges

## Geographic and socio-economic context

East Kalimantan is one of the richest provinces in Indonesia and the main contribution to the national GDP. Before palm oil and mining coal booming in early 2000, forestry, mining and gas sectors are the backbone of economic development in East Kalimantan. Because too much depending on the unrenewable natural resources, the economic growth of East Kalimantan gradually declines and, in 2016, reached the minus point because of the lowest price of coal at the global level. In 2019, Indonesia government has decided to move the capital of Indonesia from Jakarta to East Kalimantan. Currently, the government accelerate the infrastructure development of new capital.

The project will be implemented in several regions of Mahakam Delta and Adang Bay. Mahakam Delta is located on the eastern coast of the island of Borneo, in East Kalimantan province, which is one of the five provinces that has the lowest population density in Indonesia. This province is also the main contributor to the national GDP, mainly for its wealth in oil and gas. It is nevertheless aquaculture activities which constitute the main source of income for the local population. About 90% of the population depend on it for their livelihood. As a result, 54.19% of the Mahakam Delta has been converted to shrimp ponds. The majority of exports from the area are made up of tiger shrimp and white shrimp that are farmed in the delta ponds and along the Paser District's shore.

Feature 1: Land cover in mahakam delta and adang is dominated by fish pond area

Paser District is located on the east coast of East Kalimantan Province. The village of Adang Bay is located in the coastal area of this district, in Adang Bay. This area is a conservation area managed by the Ministry of Forestry (KPHP). Therefore, limited economic activities are allowed in this area. However, since the late 1990s, massive clearing for the construction of aquaculture ponds has destroyed the mangrove forest in the area. According to the District Pastor's Investment Agency, about 1,506 people live in Adang Bay. Most of them work as fishermen, fish farmers and swallowers. The village government and the community have made a strong commitment to conserve the area by adhering to the jurisdictional REDD+ approach, funded by the World Bank's FCPF or Forest Carbon Partnership Facility Project.

For clarification:

- Delta Mahakam (the region), Kutai Kartanegara District, Delta Mahakam Sub District and Delta Mahakam Ulu the village.

- Adang Bay (the region), Paser District, Long Ikis Sub District and Adang Bay the village.